## 22-24 Draft WP Calendar
PSRC Transportation Work Program: JULY 2022 - JUNE 2024 | [7 empty] | DRAFT
|  | Pre-Existing |  |  | 2022 RTP/New Work |  |  |  | 2024 Funding Framework Begins |  |  |  |  | Beginning of 2026 RTP Development |  |  |  |  | Board Action
| 2022 | [5 empty] | 2023 | [11 empty] | 2024
PROJECT | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
Regional Transportation Plan
Alignment of RTP and Funding Cycles
Update RTP Project Prioritization Framework
Board work group to determine 2026 RTP scope of work
TPB direction on scope of work for 2026 RTP
RTP development | bar: 2024 FEB to 2024 JUN
Financial Strategy Refinement
PSRC Funding
RPEC / TOC / Regional FTA Caucus Work Program*
Policy Framework for PSRC's Federal Funds | 2023 OCT: Framework for 2024 competition
FHWA Project Selection: Board Action | 2024 MAR: 2024 competition
FTA Funding Methodology Process Discussion | 2022 SEPT: tentative
FTA Project Selection | 2022 NOV: tentative; 2024 MAR: 2024 competition
Annual FTA Adjustments Process | bar: 2022 JUL; 2023 MAY to 2023 JUL; 2024 MAY to 2024 JUN
Rural Town Centers and Corridors Project Selection | bar: 2023 JUN to 2023 SEP
Transportation Alternatives Project Selection | bar: 2023 JUN to 2023 SEP
Equity Pilot Program Development | bar: 2023 JAN to 2023 MAR
Equity Pilot Program Project Selection | bar: 2023 APR to 2023 JUN
Consolidated Grant Program Regional Rankings | bar: 2022 JUL to 2022 DEC; 2023 JUL to 2023 DEC
2023-2026 TIP
RPEC / TOC / Regional FTA Caucus Work Program*
TIP Development | bar: 2022 JUL to 2022 AUG
Conduct Equity Analysis of draft TIP | bar: 2022 JUL to 2022 AUG
Relase of TIP for Public Comment | bar: 2022 SEPT
Board Action on 2023-2026 TIP | bar: 2022 OCT
Monthly TIP Amendments
Project Tracking/Rebalancing | bar: 2023 MAR to 2023 JUN; 2024 MAR to 2024 JUN
Climate: GHG Analysis and Planning
2030 Transit Networks and Service | bar: 2022 SEPT
PSRC 2030 Network Modeling and Analysis | bar: 2022 OCT to 2022 NOV
Puget Sound Regional Emissions Analysis Project | bar: 2022 JUL to 2022 DEC
Regional Electric Vehicle Collaboration Clearinghouse | bar: 2022 SEPT
Regional Electric Vehicle Collaboration Outreach | bar: 2022 OCT to 2022 DEC; 2023 MAR; 2023 JUN; 2023 DEC; 2024 MAR; 2024 JUN
Develop Climate Implementation Strategy with Partners | bar: 2022 SEPT to 2022 DEC
PSRC Board Progress Briefings | 2022 OCT: proposed; 2023 JAN: proposed
Regional Safety Plan
Work with Established Staff Committees* | bar: 2022 JUL to 2022 DEC
Explore Grant/Funding Opportunities | bar: 2022 JUL to 2022 AUG
Apply for Safe Streets for All Grant | bar: 2022 SEPT
Convene Stakeholders | 2022 NOV: tentative
Develop Scope of Regional Safety Plan | 2023 JAN: tentative
Develop Regional Safety Plan | 2023 JUL: tentative
Performance Measures and Dashboard
Align with Equity Tracker, other related monitoring efforts
Identify Measures | bar: 2022 AUG
Develop Dashboard Outline for Board Feedback | bar: 2022 SEPT
Assemble Data | bar: 2022 OCT to 2022 NOV
Publish Draft Dashboard | bar: 2022 DEC
Refinement and Updates | bar: 2023 SEP to 2023 NOV
Annual Board Briefings | bar: 2022 DEC; 2023 DEC
Active Transportation Plan Repackaging
BPAC Work Program* | bar: 2022 SEPT to 2022 DEC
ADA Transition Plan Technical Assistance
BPAC / SNTC Work Program*
Research current plans, roles and responsibilities | bar: 2023 JAN to 2023 MAR
Board Briefing and Discussion | 2023 APR: proposed
Annual Transit Integration Report
TOC / SNTC Work Program*
Report Development | bar: 2022 JUL to 2022 NOV; 2023 JUL to 2023 NOV
Publish Report | bar: 2022 DEC; 2023 DEC
Future of High Capacity Transit
TOC / Regional TOD Committee Work Program*
Regional Convening | 2023 NOV: proposed
Data Collection, Analysis, Performance Metrics
Work with Established Staff Committees
Data collection, maintenance of viz tool, improvements | bar: 2023 JAN to 2023 DEC
Equity, EJ analysis methodology improvements | bar: 2023 JAN to 2023 DEC
RTP Financial Strategy
Collaborate with Partners on Implementation Steps | 2023 FEB: tentative
Board and Committee Support
Transportation Policy Board: Direction on all Work Plans; Quarterly Progress Reports
*Staff Committees: Data Collection, Technical Assistance, Best Practies, Input and Guidance
Regional Project Evaluation Committee (RPEC): Project Selection, Project Delivery, TIP
Transportation Operators Committee (TOC): Annual Transit Integration Report, Project Selection, TIP
Bicycle Pedestrian Advisory Committee (BPAC): Active Transportation Plan Repackaging, ADA Transition Plan
Special Needs Transportation Committee (SNTC): ADA Transition Plan
Transportation Demand Management Committee (TDM): TDM Expansion
Regional FTA Caucus: Project Selection, Project Delivery, TIP
Freight Advisory Committee
Regional Traffic Operations Committee
Regional Staff Committee: Integration with VISION 2050
Note: other external collaborations / committees not reflected here
x
x
x
x
x
x
x
x
x
x
x
x
x
x
x